## Team 13
Week | Task
16 - 27 October | Study and understand the reuirements of the project. Discuss on team roles and technologies which would be required to build the project.
27-31 October | Project changed. 1. Study the documents and code base and get an idea about the various components associated with the project. 2. Discuss and decide the role of each team member in the project.
31October - 7November | 1. Understand the previous development team documentation and intricacies of the apps. 2. Create Project Charter document. 3. Create Project Plan document. 4. Create Software Requirement Specification document. 5. Create Software Design Specification document.
2016-11-07 | 1) a. Get Android app to build with latest gradle and sdk. b. Walkthrough of the application for better understanding. 2) a. Get iOS app to build and walkthrough of the app for better understanding. b. Study the feasibility of porting the app from Objective-C to swift 3.0 3) Get familiar with swing.

## Arpit
Week | Task | Percentage complete | Hours Worked
16 - 27 October | 1. Analyzed and studied the requirement and feasibility of the project. 2. Meeting with faculty advisor and discussing project requirements. 3. Discuss on team roles and technologies which would be required to build the project | 100% | 10hrs
27-31 October | 1. Team was advised that our project is changed but the technologies used will be simmilar. Meet with Faculty advisor twice in a week to get better understand and expectations from the project. 2. Studied the application in hand and analyzed the work that need to be done in achieving the completion of project. 3. Divided team roles and studid components of iOS application. Present application is in Objective -c and needs to be written in Swift 3. 4.Studied the approach to go ahead with conversion of existing code or writing it from scratch. | 95% | 11hrs
31October - 7November | 1.Meet with the sponsor, did requiremnt gathering for the iOS application. 2.Did a walk through of the app with Sponsor to get better understanding as to what needs to be enhanced or added. 3. Reviwed the content of the iOS mobile application to remove data which is no more usefull for the app. 4.Updated XCODE to support swift 3 and started with basic tutorial of conversion of each header and method files to swift files. 5.Worked on completion of Project charter with all the details from the meeting with the sponsor and aded relevant details to charter. 6. Started working on Software Design Specification document. | 100% | 13hrs
7 November - 14 November. | 1.Working on final draft of Software DEsign Specification documents. 2.Meet with faculty advisor to gather assests required for the project like images and logos. 3. Discussed few approaches for developing the iOS application in swift. 4.Started working on the changes in the storybord in xcode. | 95% | 12.5 hrs

## Gowtham
16 - 27 October | 1) Set up an initial meeting with the sponsor. 2) Discussed about the idea of the project, the motivation to do it. Gathered the high level requirements of the projects. 3) Decided about the scope of the project. 4) Explored various tools and technologies that are available to build the system. Finalized the platform and technologies that would be used. | 100% | 12
27-31 October | 1) The project idea was modified. But the domain of the system remained the same. Decided that application had to be built for iOS and Android. To achieve platform independence, agreed to build the desktop application in Java Swing. The Java application would control the contents of either of the applications. 2) Finalized on the meeting time with the sponsor. 3) Identified skills of individual team members and decided upon the roles accordingly. 4) Got the existing code base from the sponsor and identified and analyzed the subcomponents in the system. 5) Estimated the time and effort required to complete the project. Discussed the tentative project completion date and formed a project timeline. | 90% | 10
31October - 7November | 1) Gathered the requirements for the Desktop Java app. Documented the requirements for future reference. 2) Existing iOS and Android app were built and presented to the sponsor and the mentor. Listed all the modifications to be done. Discussed about adding new features which would improve the usability of the application. 3) Started learning Java Swing. Created basic framework for the application. 4) Request the mentor to provide a server space to host the xml files. 4) Completed the project charter. 5) Started working on Software Requirements Specification. | 100% | 11
7 November - 14 November. | 1) Created a basic prototype with minimal screens for Java Swing app. 2) Decided to host the server on reahat servers initially for development purposes. 3) Completed the draft of Software Requirements Specification. 4) Got a thorough estimate of the time required to create the desktop app. Created a final timeline for the development of the application by breaking down the requirements and identifying the individual components and estimating the time required to build each of the component. | 95% | 13

## Mihir
Week | Task | Percentage complete | Hours Worked
16 - 27 October | Studied, analysed and understood the requirements of the old project. Discussed with the team, on team roles and technologies which would be required to build the project. | 100 | 11
27-31 October | Had a meeting with sponsor and understood the new project, analyzed the new requirements . Had a discussion with the team on the team roles. I was assigned to build the Android App before the next meeting | 100 | 11
31October - 7November | Did gradle upgrades and modified manifest file to build the Android App. Was able to build the app. Ran the application to have a look and feel of what app does, what part of app is not working properly. Got database exceptions while running the application. Met the IHO sponsor, understood the new requirements and enhancements, suggested few changes for the enhancements. Started working on creating Project Plan (20%) outline. | 90 | 13
7 November - 14 November. | Analyzed the requirements thoroughly. Discussed on the over all development approach and prepared an outline of the project plan. Highlighted the challenges and Contributed in preparing final version of Project Plan Document (50%). Also worked on creating Software Requirements specification document (30%) and Software Design Documents (30%). | 100 | 12

## Sindhu
Week | Task | Percentage completed | Hours
October 16 - October 27 | 1. Carefully studied and analysed the requirements of the proposed project idea. 2. Set up meeting with the sponsor and discussed the requirements in more detail. 3. Discussed the tools and technologies required to develop the applications. | 100% | 12
October 27 - October 31 | 1. The project idea was modified to create enhancements to the existing ASU IHO application. The new requirements were studied. 2. Discussed the roles and responsibilities of each team member. 3. Was assigned to develop the desktop application using Java Swing to update the content on the mobile application. | 100% | 10
October 31 - November 7 | 1. Set up meeting with the sponsor from IHO who discussed the detailed requirements. 2. The requirements for the Java Swing application were noted down. 3. Started with the Oracle documentation of Java Swing tutorials. 4. Worked on the project management plan 5. Started working on the SRS document | 100% | 13
November 7 - November 14 | 1. Finished the SRS document. 2. Decided the date of delivery of the prototype with the sponsor and started working on i | 80% | 11

## Sweta
Week | Task | Percentage complete | Hours Worked
16 - 27 October | 1. Communicated with the sponsor to fix a time for weekly meeting because of confliting schedules of the sponsor and team. 2. Before the first meeting with Dr. Timoth Lindquist, understood the project requirements and project motivation from all the documents provided. Also analyzed the existing applications and did research on how adaptive apps can be made. 3. In the first meeting the project was changed to developing IHO mobile systems. 4. Study and understand the requirements of the project. 5. Discuss on team roles and technologies which would be required to build the project. 6. Created meeting minutes and sent to all the people present in the meeting. | 100% | 12hrs
27-31 October | 1. After intial discussion about roles, I was assigned the role of faciitator and team lead. I was responsible for all communications with the team and the sponsor. 2. Also responsible for working on iOS development portion of the project. 3. Team was advised that our project is changed but the technologies used will be similar. Meet with Faculty advisor twice in a week to get better understand and expectations from the project. Studied the application in hand and analyzed the work that need to be done in achieving the completion of project. Divided team roles and studid components of iOS application. Present application is in Objective -c and needs to be written in Swift 3. Studied the approach to go ahead with conversion of existing code or writing it from scratch. 4. Created meeting minutes and sent to all the people present in the meeting. 5. Cretaed user stories in Backlog in Taiga. | 100% | 13hrs
31October - 7November | 1. Met with client Juile Russ from Institute of Human Origins and did requiremnt gathering. 2. Did a walk through of the app with client to get better understanding as to what needs to be enhanced or added. 3. Reviewed the content of the iOS mobile application to remove data which is no more usefull for the app. 4. Updated XCODE to support swift 3 and started with basic tutorial of conversion of each header and method files to swift files. 5. Worked on completion of Project Plan with all the details mainly on Work Breakdown Structure. 6. Started working on Software Design Specification document. 7. Created elaborate meeting minutes as this was an important meeting with many decision and key points and sent to all the people present in the meeting. 8. Created first sprint and assigned tasks. | 95% | 13hrs
7 November - 14 November. | 1. Working on Software design specification document. While preparing the documents we realized of few more questions with the sponsor. We aim to complete our Softwrae Design Specification document by 15th of november. 2. Clarified doubts with faulty advisor. 3. Decided on atimeine for first prototype. 4. Gathered all assests of the project. 5. Started working the iOS code. 6. Created meeting minutes and sent to all the people present in the meeting. 7. Updated taiga. | 95% | 11.5 hrs