## Team 13
Week | Task | Percentage complete
Week 1 | 1. Work on Vision document by assigning task to all the requirents. 2. Gather feedback from SDS , SRS , Project charter and Project plan, and work on improvemnet. 3. Created new Stories in Tiaga for all the Requirements. 4. Created Tasks in Taiaga for each of the user stories. | 100%
Week 2 | 1. Received feedback about the vision document. 2) Started working on createing a Java Swing prototype. 3) Designed the workflow of swing app to look have a user interface similar to to that of a mobile screen. 4. Deduce the best way forward to write the code in swift, options were to use a conveter or write from scratch. Understand the time required and limitations in both the methods. | 95%
Week 3 | 1. Created Uesr Interface to perform User Authenticationto log into the app. 2) Created JFrames and JPanel to have several buttons such as 'news and events', 'field notes' etc. 3) Implemented button listener to enable navigation from one JFrame to another. 4.Using converter to build one functionality of the iOS application, this was our feasibility testing. 5. Incorporate the images and links provided by Julie Russ in the code base. | 100%
Week 4 | 1. Effort required form the converter was too much , discussed this with sponsor and decide to go ahead by writing code from scratch in swift . 2. Going ahead we will be starting a new project and will seek help from objective - c code. 3) Create Independent JFrames for serveral individual screens such as 'News and Events', 'Field Notes', 'Donate Page', 'Gallery', 'About Page', 'Connect'. 4) Implemented Card Layout to mimik mobile screen for each of these individual JFrames. 5) Created JList for Field Notes and News and Events to display the list of event and news. | 100%
Week 5 | 1. Working on completiong of two button fucntionality.(About and donate) 2.Also working on revision of vision document. 3) Created Frames to display individaul list items from News and Events and Filed Notes page. 4) Provided buttons to edit and view and delete the individual list items. 5) Implemented button listeners to peform appropriate user actions. 6. Provided buttons to edit and view and delete the individual list items. 7) Implemented button listeners to peform appropriate user actions. | 40%

## Sweta
Week | Task | Percentage complete | Hours Worked
Week 1 | 1. Worked on the feedback of previous semester. 2. Worked on Vision document. 3. Created class diagram for iOS and Android for Vision document and Software Design Specification. 4. Worked on restructioning of documents. | 100% | 12hrs
Week 2 | 1. Researched different converters and plug in available for xcode which helps in converting in Objective-C to swift. 2. Tried the different converters. 3.Deduce the best way forward to write the code in swift, options were to use a conveter or write from scratch. Understand the time required and limitations in both the methods. 4. Worked on Taiga. | 100% | 13hrs
Week 3 | 1. Discussed the research with Professor Lindquist and then zeroed down on one converter swiftify. Using converter to build one functionality of the iOS application, this was our feasibility testing. 2. Incorporate the images and links provided by Julie Russ in the code base. | 100% | 16hrs
Week 4 | 1. Effort required form the converter was too much , discussed this with sponsor and decide to go ahead by writing code from scratch in swift . 2. Going ahead we will be starting a new project and will seek help from objective - c code. 3. Started with MainViewController and Main page. | 85% | 14hrs
Week 5 | 1. Working on Navigation controls and overall layout of app. 2. Continue work on Main Page. 3. Will start work on News and Events | 40% | 10hrs (ongoing)

## Gowtham
Week 1 | 1) Worked on Vision Document. 2) Created new Stories in Tiaga for all the Requirements. 3) Created Tasks in Taiaga for each of the user stories. | 100% | 11hrs
Week 2 | 1) Received feedback about the vision document. 2) Started working on createing a Java Swing prototype. 3) Designed the workflow of swing app to look have a user interface similar to to that of a mobile screen. | 100% | 10hrs
Week 3 | 1) Created Uesr Interface to perform User Authenticationto log into the app. 2) Created JFrames and JPanel to have several buttons such as 'news and events', 'field notes' etc. 3) Implemented button listener to enable navigation from one JFrame to another. | 100% | 13hrs
Week 4 | 1) Create Independent JFrames for serveral individual screens such as 'News and Events', 'Field Notes', 'Donate Page', 'Gallery', 'About Page', 'Connect'. 2) Implemented Card Layout to mimik mobile screen for each of these individual JFrames. 3) Created JList for Field Notes and News and Events to display the list of events and news. 4) Demonstrated the app to the client, the sponsor and the team to receive feedback on the same. | 95% | 13 hrs
Week 5 | 1) Created Frames to display individaul list items from News and Events and Filed Notes page. 2) Provided buttons to edit, view and delete the individual list items. 3) Implemented button listeners to peform appropriate user actions. | 80% | 9 hrs (on going)

## Arpit
Week | Task | Percentage complete | Hours Worked
Week 1 | 1. Work on Vision document by assigning task to all the requirents. 2. Gather feedback from SDS , SRS , Project charter and Project plan, and work on improvemnet. | 100% | 10hrs
Week 2 | 1. Deduce the best way forward to write the code in swift, options were to use a conveter or write from scratch. Understand the time required and limitations in both the methods. | 95% | 11hrs
Week 3 | 1. Using converter to build one functionality of the iOS application, this was our feasibility testing. 2. Incorporate the images and links provided by Julie Russ in the code base. | 100% | 13hrs
Week 4 | 1. Effort required form the converter was too much , discussed this with sponsor and decide to go ahead by writing code from scratch in swift . 2. Going ahead we will be starting a new project and will seek help from objective - c code. | 95% | 12.5 hrs
Week 5 | 1. Working on completiong of two button fucntionality.(About and donate) 2.Also working on revision of vision document. | 50% | 7(on going)

## Mihir
Week | Task
16 - 27 October | Studied, analysed and understood the requirements of the old project. Discussed with the team, on team roles and technologies which would be required to build the project.
27-31 October | Had a meeting with sponsor and understood the new project, analyzed the new requirements . Had a discussion with the team on the team roles. I was assigned to build the Android App before the next meeting
31October - 7November | Did gradle upgrades and modified manifest file to build the Android App. Was able to build the app. Ran the application to have a look and feel of what app does, what part of app is not working properly. Got database exceptions while running the application. Met the IHO sponsor, understood the new requirements and enhancements, suggested few changes for the enhancements. Started working on creating Project Plan outline.
7 November - 14 November. | Analyzed the requirements thoroughly. Discussed on the over all development approach and prepared an outline of the project plan. Highlighted the challenges and Contributed in preparing final version of Project Plan Document. Also worked on creating Software Requirements specification document and Software Design Documents.

## Sindhu
Week | Task | Percentage completed | Hours
October 16 - October 27 | 1. Carefully studied and analysed the requirements of the proposed project idea. 2. Set up meeting with the sponsor and discussed the requirements in more detail. 3. Discussed the tools and technologies required to develop the applications. | 100% | 12
October 27 - October 31 | 1. The project idea was modified to create enhancements to the existing ASU IHO application. The new requirements were studied. 2. Discussed the roles and responsibilities of each team member. 3. Was assigned to develop the desktop application using Java Swing to update the content on the mobile application. | 100% | 10
October 31 - November 7 | 1. Set up meeting with the sponsor from IHO who discussed the detailed requirements. 2. The requirements for the Java Swing application were noted down. 3. Started with the Oracle documentation of Java Swing tutorials. 4. Worked on the project management plan 5. Started working on the SRS document | 100% | 13
November 7 - November 14 | 1. Finished the SRS document. 2. Decided the date of delivery of the prototype with the sponsor and started working on i | 80% | 11